## Slide 1: Glounthaune Knotweed Eradication Plan
GTTC Survey Results
28th October 2014
Plan
Budget

## Slide 2: Introduction
Following a meeting 22th October with CCC and the Glounthaune Tidy Towns (GTTC) Knotweed Sub-committee it was agreed:
GTTC would survey the extent of the problem
CCC would investigate methods and resources
GTTC/CCC would meet 5 Nov14 (revised to 17 Nov 14) to review and plan a course of action

## Slide 3: Survey Methodology
A visual/quantities survey between Killacloyne Bridge and Bury’s bridge was undertaken
All identified areas of knotweed infestation sites key parameters recorded in line with UK guidelines and databased
Estimates of stem height, thickness, density, infestation area, and infestation area usage and perceived ownership logged

## Slide 4: Limitations to Methodology
Due to extensive infestation on Irish rail property it was not possible to accurately log all sites and observations are probably underestimated
Areas accuracy of any one site is better than +_20%
Area estimates do NOT include a 7m boundary to allow for lateral spreading.
Due to cutting of roadside verges some infestations may not have been visible
Stem number estimates are made from a number of random samples using a 1/3m2 measuring template and counting stems in around 12.5% of identified roadside sites

## Slide 5: Summary Key Numbers
GTTC estimate Knotweed infestation Area as 0.624 Hectares (6260m2)
This comprises an estimated 168,500 plants in 75 sites
Sites range from single stems to over 600m2
Primary locations are along roadsides and Railways with some evidence of spreading into adjacent private property
66% by area is on CCC property, 25% on Irish Rail , 6% straddle the boundary between IR/CCC and 2% on private property

## Slide 6
Chart: Glounthaune Knotweed Survey Infestation Area m2 by Primary Owner 28Oct14
| CCC | IR | AH | IR/CCC | RG
 | 4113.75 | 1572 | 93 | 400 | 62

## Slide 7
Chart: Glounthaune Knotweed Survey Histogram Infestation Area m2 by Site Size 28Oct14
| <1 | 1 to <10 | 10 to <100 | 100 to <333 | 333 to <1000
 | 10.75 | 85 | 1460 | 2585 | 600

## Slide 8
Chart: Glounthaune Knotweed Survey Histogram Number Sites of Infestation by Owner
| CCC | IR | AH | IR/CCC | RG
 | 35 | 24 | 5 | 8 | 2

## Slide 9
Chart: Glounthaune Knotweed Survey Histogram No Sites Vs. Site Size m2 28Oct14
| <1 | 1 to <10 | 10 to <100 | 100 to <333 | 333 to <1000
 | 12 | 16 | 32 | 12 | 1

## Slide 10
Chart: Glounthaune Knotweed Survey No. infestation Sites by Site Type 28Oct 14
| road verge | hedgerow | farmland | railway embankment | landscaped area | roundabout | park | housing | pond | stream | Industrial | sea front | car park | garden
 | 40 | 0 | 0 | 32 | 9 | 0 | 1 | 0 | 8 | 0 | 2 | 0 | 0 | 5

## Slide 11: Glounthaune Knotweed Eradication Plan
Key Objectives, Methods

## Slide 12: Key Objectives
Make Glounthaune a Knotweed free area in 3/5 years
100% of site under treatment by end 2015
Stop practices that spread infestation end 2014
Commence treatment in spring 2015
Confirm plan and budget for 2015 end November 2014
Mobilize the community, owners and manpower

## Slide 13: Methods of control
4 methods of control identified
Bury and cover – impractical given in place infrastructure and required budget
Foliar Spray – works, but takes several seasons
Stem Injection – very effective, requires specialist injector gun, safe but labour intensive
Cut and pour – very effective, but labour intensive: problem with cut stems disposal

## Slide 14: Our Proposal
Stem injection on roadside adjacent site
Foliar spray of restricted/difficult sites - commencing spring
Experiment with cut and pour on one site
Labeling of all infected sites per Kerry example
Immediate cessation by CCC of practice of flailing roadside knotweed infestations and CCC to gather up flaid material and dispose of safely.

## Slide 15: Methodology CCC
Sign all sites and fnalise treatment
  CCC to procure site notices
Safety paramount
  Work in teams of 3 – 1 member responsible for safety
Spray where safety and accessibility problematic
  Spray spring and early autumn and repeat annually
  Sub-contract spraying to professionals: use height to spray down on foliage
  Team of 3: 1 sprayer, 1 operator, 1 safety
Stem Inject all other areas
  Teams of 3, 2 injectors/1safety and clearer
  Target 27m2/hr
Resurvey October 2015 and report

## Slide 16: Japanese Knotweed Under Treatment
 | Year | Spring | Summer | Stem Inject | Foliar Spray | 
2015 |  |  |  |  |  | 
2016 |  |  |  |  |  | 
2017 |  |  |  |  |  | 
Do not cut, remove or spread material from this site.
Legal penalties apply –
European Communities (Birds and Natural Habitats 2011.
Cork County Council
Glounthaune Tidy Towns
Committee
Notice
Fallopia Japonica

## Slide 17: Methodology IR/IRCCC Sites
Meet IR with CCC and establish joint approach
Establish joint plan of action

## Slide 18: Other sites
GCTT to work with Ashborne House and Rockgrove and offer to stem inject.
NRA: CCC/GCTT to approach. GCTT could stem inject site with appropriate safety measures.

## Slide 19: Budget Cost
Budget Summary Euros |  |  |  |  |  |  | 
 | CCC | IR | AH | IR/CCC | RG | NRA | Total
2015 | 4475 | 2463 | 126 | 416 | 84 | 27 | 7565
2016 | 2974 | 2463 | 49 | 416 | 33 | 10 | 5934
Capital 2015 | 1750 | 0 | 0 | 0 | 0 | 0 | 
Costs include material, professional spraying, height hire,
Labour for injecting costed at €25/hr.
Capital cost includes cost of two injectors, spare needles, protective
equipment + misc budget of €250
All items will be billed without mark-up to CCC.
Assumed CCC will procure and provide signage to agreed specification

## Slide 20
 | 2015 Budget Knotweed Eradication Glounthaune |  |  |  |  |  |  |  | 
Materials |  | CCC | IR | AH | IR/CCC | RG | NRA | Total | 
 | Area Estimate | 4114 | 1572 | 93 | 400 | 62 | 20 | 6261 | 
 | Spray | 50% | 100% | 0% | 100% | 0% | 0% | 64% | Estimate
 | Stem Inject | 50% | 0 | 100% | 0% | 100% | 100% | 36% | Estimate
 | Stem density | 27 | 27 | 27 | 27 | 27 | 27 |  | Stems/m2
 | Inject Insecicide | 111 | 0 | 5 | 0 | 3 | 1 | 121 | Litres
 | Spray 10l/ha | 10 | 8 | 0 | 2 | 0 | 0 | 20 | 2 sprays
 | Cost/litre € | 8 | 8 | 8 | 8 | 8 | 8 | 48 | Co-op
 | Herbicide Cost | 971 | 63 | 40 | 16 | 27 | 9 | 1125 | €
 | Height Hire | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 
 | Total Materials | 1971 | 63 | 40 | 16 | 27 | 9 | 1125 | 
Labour Estimate |  |  |  |  |  |  |  |  | 
Spraying | Spring | 2 | 3 |  | 0.5 |  |  |  | days
 | Safety | 4 | 6 |  | 1.0 |  |  |  | 
 | Late Summer | 2 | 3 |  | 0.5 |  |  |  | 
 | Cost Per day | 200 | 200 | 200 | 200 | 200 | 200 |  | €
 | Sub total spraying | 1600 | 2400 | 0 | 400 | 0 | 0 |  | €
Injection | Area m2 | 2057 | 0 | 93 | 0 | 62 | 20 |  | m2
 | No Hours | 76 | 0 | 3 | 0 | 2 | 1 | 0 | hrs
 | Cost per hour | 25 | 25 | 25 | 25 | 25 | 25 |  | €
 | Labour Injection | 1905 | 0 | 86 | 0 | 57 | 19 | 2067 | €
 | Total Variable | 4475 | 2463 | 126 | 416 | 84 | 27 | 7592 | €
 | Capital | 1750 |  |  |  |  |  |  | 
 | Capital Costs |  |  |  |  |  |  |  | 
 | Injectors by 2 | 1100 |  |  |  |  |  |  | 
 | spare needles | 100 |  |  |  |  |  |  | 
 | Protective Gear | 300 |  |  |  |  |  |  | 
 | Misc | 250 |  |  |  |  |  |  | 
 |  | 1750 |  |  |  |  |  |  | 

## Slide 21: Glounthaune Community Association – Tidy Towns Committee
Run by professionals – with extensive chemical and safety expertise
History of involvement and project delivery
“Pride of Place” Winner
Committed to making Glounthaune a better environment